## Master-2025
| Table Information Extraction |  |  |  | 2.2025 |  |  |  | 3.2025 |  |  |  | 4.2025 |  |  |  | 5.2025 |  |  |  | 6.2025 |  |  |  | 7.2025 |  |  |  | 8.2025 |  |  |  | 9.2025 |  |  |  | 10.2025 |  |  |  | 11.2025 |  |  |  | 12.2025
# | Task | Member | Status | % | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Literature Review/Survey
1.1 | + Table Detection
1.1.1 | - TATR |  | Done | 100% | bar: 2.2025 1
1.1.2 | - TDeLTA |  | Done | 100% | bar: 2.2025 1
1.1.3 | - Text & Layout based methods |  | Not yet
1.2 | + Table Structure Recognition
1.2.1 | - CascadeTSRDet, TFLOP |  | Done | 100% | bar: 2.2025 2
1.2.2 | - TATR |  | Done | 100% | bar: 2.2025 2
1.2.3 | - SEMv3, UniTable, UniTabNet |  | Done | 100% | bar: 2.2025 2
1.2.4 | - Layout based methods |  | Not yet
1.3 | + Semantic Analysis
1.3.1 | - LLM |  | Doing | 30%
1.3.2 | - ???
2 | Evaluation SOTA
2.1 | + TATR - Table Detection & Table Structure Recognition | bar: 2.2025 3
2.1.1 | - Install | bar: 2.2025 3
2.1.2 | - Run Samples | bar: 2.2025 3
+ Yooz Samples
2.2 | + CascadeTSRDet - Table Structure Recognition | bar: 3.2025 4
2.2.1 | - Install |  | Done | 100% | bar: 2.2025 3
2.2.2 | - Run Samples by Pre-trained model |  | Done | 100% | bar: 3.2025 2
2.2.3 | - Evaluation by Pre-trained model |  | Done | 100%
+ Yooz English Dataset | bar: 3.2025 3 to 3.2025 4
- Pre-processing
- Code
- Analysis
+ Public Dataset
2.2.4 | - Re-train model
+ Pre-processing
+ Train
+ Evaluation and Analysis
2.3 | + TFLOP - Table Structure Recognition
2.3.1 | - Install | bar: 3.2025 4 to 4.2025 1
2.3.2 | - Train | bar: 4.2025 1 to 4.2025 2
+ PubTabNet Dataset
+ FinTabNet Dataset (need change code)
2.3.3 | - Evaluation on Yooz English Dataset | bar: 4.2025 2 to 4.2025 3
+ Pretrained by PubTabNet Dataset
+ Pretrained by FinTabNet Dataset
3 | Table Detection
3.1 | + TATR - Table Detection
- Install | bar: 4.2025 1
- Run Samples by Pre-trained model | bar: 4.2025 1
3.1.1 | - Evaluation by Pre-trained model | LongDV | bar: 4.2025 1
+ Yooz English Dataset - DocLie | bar: 4.2025 1
- Pre-processing | bar: 4.2025 1
- Code | bar: 4.2025 1
- Analysis | bar: 4.2025 1
3.1.2 | - Post Processing | LongDV | bar: 4.2025 2
4 | Semantic Analysis
4.1 | - Llama 3.2 3B | LongDV | bar: 3.2025 4 to 4.2025 1
4.2 | - Mistral
5 | LLM for Table Structure Recognition | LongDV
5.1 | - Llama 3.2 3B
| + Coding & Unit Test |  | Done | 100% | bar: 3.2025 4
5.2 | - SmolDocling
| + Coding & Unit Test |  | Done | 100% | bar: 3.2025 4
6 | Propose new method
6.1 | + Ideas
6.1.1 | - Table Detection
+ How to use text and layout information more effectively?
- Network architecture
- Post-processing
6.1.2 | - Table Structure Recognition
+ How to use layout information more effectively?
- Post-processing
6.1.3 | - Semantic Analysis
+ LLM
- Llama, Mistral
+ LoRA
+ Our method
6.2 | + Implementation