## Master-2025
| Table Information Extraction |  |  | 2.2025 |  |  |  | 3.2025 |  |  |  | 4.2025 |  |  |  | 5.2025 |  |  |  | 6.2025 |  |  |  | 7.2025 |  |  |  | 8.2025 |  |  |  | 9.2025 |  |  |  | 10.2025 |  |  |  | 11.2025 |  |  |  | 12.2025
# | Task | Status | % | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Literature Review/Survey
1.1 | + Table Detection
1.1.1 | - TATR | Done | 100% | bar: 2.2025 1
1.1.2 | - TDeLTA | Done | 100% | bar: 2.2025 1
1.1.3 | - Text & Layout based methods | Not yet
1.2 | + Table Structure Recognition
1.2.1 | - CascadeTSRDet, TFLOP | Done | 100% | bar: 2.2025 2
1.2.2 | - TATR | Done | 100% | bar: 2.2025 2
1.2.3 | - SEMv3, UniTable, UniTabNet | Done | 100% | bar: 2.2025 2
1.2.4 | - Layout based methods | Not yet
1.3 | + Semantic Analysis
1.3.1 | - LLM | Doing | 30%
1.3.2 | - ???
2 | Evaluation SOTA
2.1 | + TATR - Table Detection & Table Structure Recognition
2.1.1 | - Install | bar: 2.2025 3
2.1.2 | - Run Samples | bar: 2.2025 3
+ Yooz Samples
2.2 | + CascadeTSRDet - Table Structure Recognition
2.2.1 | - Install | Done | 100% | bar: 2.2025 3
2.2.2 | - Run Samples by Pre-trained model | Done | 100% | bar: 3.2025 2
2.2.3 | - Evaluation by Pre-trained model
+ Yooz English Dataset | bar: 3.2025 3 to 3.2025 4
- Pre-processing
- Code
- Analysis
+ Public Dataset
2.2.4 | - Re-train model
+ Pre-processing
+ Train
+ Evaluation and Analysis
2.3 | + TFLOP - Table Structure Recognition
2.3.1 | - Install | bar: 2.2025 3
2.3.2 | - Train
2.3.3 | - Evaluation
3 | Propose new method
3.1 | + Ideas
3.1.1 | - Table Detection
+ How to use text and layout information more effectively?
- Network architecture
- Post-processing
3.1.2 | - Table Structure Recognition
+ How to use layout information more effectively?
- Post-processing
3.1.3 | - Semantic Analysis
+ LLM
- Llama, Mistral
+ LoRA
+ Our method
3.2 | + Implementation